## Simple Gantt Chart - BLANK
PROJECT TITLE |  | Fill In
PROJECT MANAGER |  | Fill In
COMPANY NAME |  | Fill In | [5 empty] | Denotes Critical Path - Would any tasks in Section 3 be considered part of the critical path? | [27 empty] | Answer
DATE |  | Fill In
[6 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE
TASK | TASK | TASK | START | DUE | DURATION | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9
ID | TITLE | OWNER | DATE | DATE | IN DAYS | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1
1.1 | Define scope of Showroom | Project Team 1 | Week 1 | Week 3 | 10
1.1.1 | Research teams to be involved | Project Team 1 | Week 2 | Week 2 | 5
1.2 | Work up initial budget projections | Project Team 1 | Week 2 | Week 3 | 5
1.3 | Final Scope Review | Project Team 1 | Week 3 | Week 3 | 5
1.4 | Create Risk Management Register | Project Team 1 | Week 3 | Week 3 | 2
2
2.1 | Create Project Plan via Gantt Chart | Project Team 1 | Week 4 | Week 4 | 5
2.2 |  | Project Team 1
2.3 |  | Project Team 1
2.3.1 |  | Project Team 1 | Week 7 | Week 7 | 3
2.4 |  | Project Team 1
2.5 |  | Project Team 1
3
| Project Objectives | Project Team 1 | Week 1 | Week 8
| Effort and Cost Tracking | Project Team 1 | Week 3 | Week 9 | 30
| Project Performance | Project Team 1 | Week 1 | Week 9 | 45
Project Conception and Planning
Project Launch and Execution
Project Performance / Monitoring
Vendor 2 Gas Installation
Appliances Installed
Vendor/Supplier Start Work
Obtain Building Permit
Final Punch List Created
Yes
No